## Risk Assessment
RISK ASSESSMENT AND METHOD STATEMENT
SSW-IMS-001-PRC
Revision: 002
Date: Oct, 2018
RISK ASSESSMENT
Activity | Hazard | Risk | Who is at risk | Controls in place | Risk Evaluation |  |  |  | Additional Control | Responsible person | Risk Residue
[5 empty] | S | P | RV | RL |  |  | S | P | RV | RL
TOWER STRENGTHENING WORKS
Driving to and from site | Over speeding -Vehicle breakdown | Fatality or Injuries or Permanent disabilities. | All vehicle users | -Only licensed drivers to drive company vehicle. | 4 | 3 | 12 | H | ―Abide by road traffic regulations ― Carrying passengers on back of trucks is prohibited -Vehicle inspection -No night driving, -No driving under alcohol influence. -Journey management plan -Schedule Vehicle maintenance and repair as per manufacturer (service card). | Fleet Manager and SHEQ | 4 | 1 | 4 | L
| Hijacking | Fatality or Injuries or Permanent disabilities. | All vehicle users | GPS Car track System | 3 | 2 | 6 | M | Journey management plan | Fleet Manager & SHEQ Manager | 3 | 1 | 3 | L
No night driving
Working at Height/Climbing tower, lifting of equipments | Slip, trips & fall from height, Falling objects | Fatality or Injuries or Permanent disabilities. | All people who will work at height | Working at height competent and trained riggers, All riggers must be medical fit, No one allowed to work under influence of alcohol.Fall Arrest Equipments checks and inspections prior work .Barricade the working area below the tower | 4 | 3 | 12 | H | Daily Field Level risk assessment. -No person allowed to work at height alone. -Do not climb tower when its raining or when there is high wind velocity. -Tool box talk before work -Full body Harness must be used -trained First Aider in every team | Supervisors | 4 | 1 | 4 | L
Working with power tools such as Magnetic Drill,Grinder | Electric shock,Flying particles | Injuries or Permanent disabilities. | All people who will work with power tools | Only trained and experienced person will operate tools | 4 | 3 | 12 | H | Tools inspections Only qualified electrical technician operates electrical tools | SHEQ officer & Supervisors | 2 | 2 | 4 | L
|  |  |  | Every team to have quqlified Electrical technician |  |  |  |  | Tool box talks No use of Defective tools Don’t touch bare wire at site Always ware apropriate PPE Use proper insulated tools
Working near Microwave dish | Bees sting. Exposure to EMF radiations. | Body painful, sweling and itchig. | All people working near Microwave dishes or bees nests | Fumigation Bees realocation | 4 | 2 | 8 | M | Wearing bees protective clothing Avoid working infront of MWD | Supervisors/riggers | 4 | 1 | 4 | L
Material Handling include Loading & offloading | Slip, trips, Fall objects, material or tools, | Result to: Equipment/Property damage, Physical injuries including back stain Muscle and permanent disability. | All people involved in manual handling | Inspection of work . Awareness program, Manual handling procedure | 4 | 2 | 8 | M | Heavy equipment to be carried by mechanical aid ie crane,forkal lift etc | Supervisors/riggers | 4 | 1 | 4 | L
|  |  |  | Manual handling technique training |  |  |  | M
Tower Painting | Exposure to heavy metal(lead), Fire due to its flamability | Health effects,brain and nervous system | All people involved in painting | Use of unleaded paints. Material Safety data sheets. | 3 | 2 | 6 | M | Avoiding naked flame, No Smoking at site Wearing appropriate Personal Protective Equipment(i.e eye protection, rubber gloves and respiratory protection) | Supervisors/riggers | 3 | 1 | 3 | L
|  |  |  | Good housekeeping |  |  |  | M

## Matrix
SSW-IMS-001-PRC | RISK ASSESSMENT AND METHOD STATEMENT
Revision: 002
Date: Oct, 2018
a.Likelihood/Probability | [5 empty] | b.Consequence
Level |  | Likelihood (Probability) |  |  |  | Level |  | Consequence (Hazard Effect)
4 | Invariably happen | The incident is expected to occur most of the time (i.e. every time), Will invariably happen ‑ could occur repeatedly |  |  |  | 1 | Minor | Short term of localised impact, Injury requiring medical attention or first aid
3 | Highly probable | The incident will probably occur in most circumstances (i.e. regularly, weekly), Highly probable ‑ could occur several times |  |  |  | 2 | Moderate | Prolonged but recoverable impact on the environment and commercial industries, 3 Day Injury/Temporary Disability
2 | Feasible | The incident should occur at some time (i.e. quarterly), Possible: Feasible ‑ could occur sometime |  |  |  | 3 | Major | Prolonged impact to the environment which may not be recoverable and threatens an ecological community, the conservation of species, Major Injury/Long Term Absence
1 | Might happen | The incident could occur at some time (e.g. once in 5 years), Possible: Might Happen ‑ unlikely though conceivable . |  |  |  | 4 | Catastrophic | Non-recoverable change to existing environment leading to loss of endangered species or creation of human health risk, Fatality/Permanent Total Disability (PTB)
*PTB = Permanent Total Disability
c.Risk level | [6 empty] | d.Rating key
|  | LIKELIHOOD |  |  |  |  | Rating |  | Definition
CONSEQUENCES/ SERVERITY |  | 1 | 2 | 3 | 4 |  | 13-16 | High | Stop immediately? Risk is too high and not acceptable
|  | Heard of in the Tower industry | Incident has occurred in Tigo | Happens several times per year in Tigo | Happens several times per year in a site |  | 9 -12 | Medium - High | Requires immediate attention to bring the risk down to an acceptable level
|  | 1 | 2 | 3 | 4 |  | 5-8 | Medium - Low | Requires attention to reduce the rating and regular ongoing monitoring
| 1 | 1 | 2 | 3 | 4 |  | 1-4 | Low | Low risk – Continue with existing control, however monitor for changes
| 2 | 2 | 4 | 6 | 8
| 3 | 3 | 6 | 9 | 12
| 4 | 4 | 8 | 12 | 16

## Method statement
RISK ASSESSMENT AND METHOD STATEMENT
SSW-OHS-006-TMP
Revision: 002
Rev Date: Oct, 2019
METHOD STATEMENT -
Client: MIC-Tigo Tanzania
Date on-site start: 6th Dec 2019
Due Date on-site completion: 13th Dec 2019
Hours of work: 8am-5pm
Emergency contact : NOC-0715500915 Emergency Services: Fire: 114 Police: 112 Ambulance: 112
1. Description of the work | Tower strengthening activities includes:
Angle iron bracing members (Main Diagonal,Horizontal) Including all Drilling, Cutting, Grinding, Torquing, Installation, Swapping existing/replace bolts (Same zize) - M16x60, Torque Whole Tower,
Painting replaced members, bolt, nuts and washers as per international Telecom standard,
Reinforce the foundation
Transportation of the dismantled materials (Steel members and bolts)from site to warehouse
2. Description of site Location | The site is located at Tigo Segera Tanga region
2. Method Planning
From : TIGO
Name :Damiano Philipo
Every effort will be made to obtain information to allow for the safe planning of the work following SINCRO SITEWATCH LTD safe work procedure “Tower Strengthening Works” (in preparation), for obtaining BOM and Structural Analysis. If information requested for the safe planning of the work is not obtained before work is due to start, the client must be informed and asked for a postponement. The provision of drawings and site specific information will assist in the planning and safe execution of the works. This information will not diminish the hazards but will help reduce the risks associated with the hazards. With the location of services indicated on drawings safe working practices will still be followed to avoid accidents.
The power used on sites will be provided by Onsite power
3. First Aid | First aid will be provided by SSW trained personnels. A First aid kit will be available on-site.
Accident and incident forms are provided on-site and these must be completed for every accident or incident. Completed forms must be sent to SHEQ department at Head Office who will send a copy to the client.
4. Welfare | A means of cleaning hands and face , drinking water will be available on site, and facilities for using a toilet or directions to a toilet facility nearby provided.
5. PPE requirements | PPE will be provided to the teams include Safety boots, Helmet, reflective jackets, full body harness, safety glass, gloves, Respiratory protection and Bee protecive suit
6. Sequence of work | DRIVING
§ Only drivers with valid license are permitted to drive company vehicle
§ Avoid driving when you're tired. Be aware that some medications can cause drowsiness and make operating a vehicle very dangerous.
§ Drive following road traffic legislation
§ It is prohibited driving under the influence of alcohol and drugs
§ Avoid night driving
§ Speed limit should be adhered
§ It is advised to wear seat belt, it helps in case of emergence
§ Every vehicle should be installed with safety equipment such as fire extinguisher and first aid kit.
STRENGTHENING THE TOWER MEMBERS, TORQUEING AND BOLTS REPLACEMENT etc
§ Workers working at height will include climber’s certification, medical fit and training.
§ Fall-Arrest Harness System and the following procedures will be followed when working at height
§ Each anchor point must be inspected.
§ Each anchor point must be located so that a lanyard can be attached before the person moves into a position that they may not fall.
§ Access to the fixing point will be by a ladder which will be fixed to prevent slipping.
§ No person is allowed to use the system alone.
§ No under ground activities should be done during the replacement of tower members and other at height accesories.
§ Emergency procedures should there be a fall to retrieve the fallen person.
STEEL CUTTING AND DRILLING USING POWERED EQUIPMENTS
§ Only well trained and experienced person will be allowed to operates powered tools
§ LOTO procedure should be adhered
TOWER PAINTING
§ All workers painting with brushes are required to wear the appropriate and proper personal protective equipment (PPE). This includes eye protection, rubber gloves and respiratory protection in the case of alkaloid-(oil) based paint.Proper precautions related to safety body harness use must be followed by avoiding paint drops on it since it deteriorates the harness.
7. Supervision arrangements and responsibilities | SINCRO SITEWATCH Ltd SHEQ officer and supervisor will be designated prior to works commencing. Will ensure all personnel working for the work are competent and fit for the work.
The SINCRO SITEWATCH Ltd supervisor will control all site operations. All operatives will be fully instructed and informed with regard to all works they are involved in.
Monitoring of all aspects of the works, processes and procedures will be undertaken by Sincro Sitewatch SHEQ personnel and Project Manager .
8.Materials and Tools | All equipment will be checked before commencing any work for maintenance services and records.
Regular maintenance of equipment such in order to increase safety and minimize environmental impact.
List of materials and tools 1. Vehicles 2. Grinding disc 3.cutting disc 4.Angle grinder 5.Steel members 6.Torque wrench 7.Paints
9.Environmental Controls | Noise will be kept to a minimum. Silenced tools and generators will be used with the use of plywood screens if the assessment shows this to be a noise sensitive area. After work completion all waste paints and materials storage areas on site must be clearly identified and returned back to head office for proper disposal. Drip trays will be used under plant to prevent oil spills onto the ground surface. Site will be secured by means of Herras fencing and suitable warning and advisory signage displayed.
10. Emergency procedures | The site emergency procedures will be issued at induction training and are as follows:
In the event of a fire or explosion all personnel must evacuate the site immediately.
The supervisor will contact the emergency services giving full details of the site – location, etc.
In the event of an employee sustaining an injury he must be attended to immediately by a qualified first-aider.
An initial report on the incident will be written by the supervisor.
This report must be conveyed to SINCRO SITEWATCH Ltd SHEQ personel as soon as possible, who will notify the client.
11. Control of site operations
SINCRO SITEWATCH Ltd supervisor will control all site operations, in liaison with Client.
Work will not commence until everyone present has attended an induction, and personal protective equipment has been issued. All tools and equipments must be checked before use for maintenance records, test certificates and certificates of test and thorough examination.The SINCROSITE WATCH Ltd tools register will be used to keep a check on records supplied. Weather conditions such as heavy rain, lightning, strong winds will cause works to stop until an improvement in conditions. All workers will work in a safe and healthy manner and co-operate with other persons and the SINCRO SITEWATCH Ltd Supervisor to ensure safe delivery of the works
12. Site finish and handover | All removed steel members, bolts and other materials will be transported in acceptable manner, and all wastes disposed in a proper way. The method of disposal and the quantiy disposed should be recorded

## Manning List
RISK ASSESSMENT AND METHOD STATEMENT
SSW-OHS-006-TMP
Revision: 002
Rev Date: Oct, 2019
MANNING LIST
Team | No | Name | Responsibility/Role | Qualification required | Medical Examination | WAH | IFAT
| 1 | William Jeremiah | Supervisor/First Aider | Mechanical Engineering/IFAT | Fit | N/A | Ok
| 2 | Makala Athuman | Rigger | Fall arrest and basic rescue | Fit | Ok | N/A
| 3 | David Wambura | Rigger | Fall arrest and basic rescue | Fit | Ok | N/A
| 4 | Michael Mwanga | Rigger | Fall arrest and basic rescue | Fit | Ok | N/A

## Approval Cover
RISK ASSESSMENT AND METHOD STATEMENT
SSW-OHS-006-TMP
Revision: 002
Rev Date: Oct, 2019
PROJECT NAME: TOWER STRENGTHENING
No | Site ID | Site Name | Region
1 | TNG 001 | Segera | Tanga
MS prepared by:
PROJECT SUPERVISOR –
Name: William Jeremiah | Signed: | Date: 5 Dec 2019
Approved by:
SHEQ – SINCRO
Name: Arcado Shayo | Signed: | Date: 5 Dec 2019
Approved by:
PROJECT - TIGO
Name: | Signed: | Date:
Approved by:
HSE-TIGO
Name: | Signed: | Date: